## System Management Methodology Overview for Implementation Roadmap

### Definition

System Management involves the following main areas necessary to support SAP:

- Planning the technical infrastructure

- Installation and configuration of hardware

- Network, servers, disk storage, printers, etc.

- Installation and configuration of software

- R/3, CCMS, TMS, SAPRouter, etc.

- System administration and support of:

- SAP

- Database

- Operating System

- Network

- Output management (printers, fax)

- System testing to ensure that the technical environment can support the business requirements with optimal performance.

- Define service level agreement and disaster recovery procedures

- Thorough backup and recovery procedures.

- Training of technical, operations, and support staff

### Purpose

The purpose of Systems Management is to install, configure, administer, and maintain the technical infrastructure necessary for the implementation and operation of the SAP software. This also includes realization of optimal performance, monitoring procedures, system recoverability, and high availability.

### System Management Overview Table

| Ph a s e | Work package or ”Activity group” | Activities | Tools or Key Accelerators | Roles | Deliverables | (optional) System/ Environment |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Define Technical Implementation Standards | Define Change Request Management, Support Package Strategy, and Upgrade Strategy | Change and transport request form, Change request log template, Misc links to SAPNet | Business Process Team Lead, Customer Project Manager, TeamSAP Project Manager, Technical Team Lead, System Administrator, Technical Consultant | Procedures for Change Request Management, Early understanding of support package and upgrade processes |  |
| 1 | Define System Landscape | Determine the Required Systems and Clients, Define Transport Strategy, | System Landscape Made Easy Guide, IT Infrastructure Document, Client Change Settings Flowchart, Verify the Use of Preconfigured Systems, Change and Transport Request Form, Misc links to SAPNet | Customer Project Manager, TeamSAP Project Manager, Technical Team Lead, Technical Consultant, System administrator | Design of the company’s system landscape, including its setup and maintenance strategy |  |
| 1 | Technical Requirement Planning | Complete Technical Questionnaires, Define Technical Infrastructure Needs, Size and Order the Hardware and the Remote Network Connection | IT Infrastructure Document, R/3 Security Manual, Quick Sizing Tool on SAPNet, Network System Key Issues, Network Load Release 4.0, R/3 System Installation Template, rcPack: Service Package Details, Misc links to SAPNet | System, Database, Operating System, and Network Administrators; Technical Team Lead, Technical Consultant, Customer Project Manager, TeamSAP Project Manager | Definition of the technical infrastructure needs, Detailed sizing of SAP system, Technical infrastructure requirements approved, Hardware and remote connection ordered |  |
| 2 | Develop System Environment | Create the Technical Design- document the physical network, systems layout, printing infrastructure, and desktop management strategy. | IT Infrastructure Document, R/3 Security Manual, Printing Questionnaire, Guide to Printing Infrastructure, Classification of R/3 Integration Projects, Misc links to SAPNet | System, Operating System, and Network Administrators; Technical Team Lead, Technical Consultant, Customer Project Manager, TeamSAP Project Manager, Business Process Team Lead | Infrastructure documented in the IT Infrastructure Document, Security documented in the R/3 Security Manual |  |
|  |  | Set Up the Development Environment- install the hardware, configure and secure the system, set up printing services and the remote connection | IT Infrastructure Document, R/3 Security Manual, Misc links to SAPNet | System, Database, Operating System, and Network Administrators; Technical Team Lead, Technical Consultant, Customer Project Manager, TeamSAP Project Manager, Business Process Team Lead | Hardware and software properly installed, Printing services and remote connection set up | Development system environment ready to support project team |
|  |  | Maintain System Administration Procedures | IT Infrastructure Document, R/3 Security Manual, System Administration Workshop Outline, System Administration Checklists, List of Organization Reports, Misc links to SAPNet | System, Database, Operating System, and Network Administrators; Technical Team Lead, Technical Consultant | Technical staff trained and capable to support the IT infrastructure, CCMS is configured, Backup strategy defined |  |
| 3 | System Management | Develop System Test Plans for printing and faxing, system administration, failure test, volume test, and stress test | Technical Failure Testing Checklist, Volume Test Sample Plan, Volume Test Plan / Stress Test Plan, Performing a Stress Test, Stress Test Sample Plan, Stress Testing Strategy, Perform Stress Test, Misc links to SAPNet | System, Database, Operating System, and Network Administrators; Technical Team Lead, Technical Consultant, Customer Project Manager, TeamSAP Project Manager, Business Process Team Lead, Project Sponsor | Final test plans are defined |  |
|  |  | Define Service Level Commitment- determine scenarios and disaster recover procedures, establish service level commitment | SAP GoingLive Check, SAP EarlyWatch Service, Chapter 2: Disaster Recover in the System Administration Made Easy Guide in the Knowledge Corner, Misc links to SAPNet Chapter 2: Disaster Recovery in the System Administration Made Easy | System, Database, Operating System, and Network Administrators; Technical Team Lead, Technical Consultant, Customer Project Manager, SAP Technical Consulting Manager, Business Process Team Lead, Project Sponsor | Failure scenarios risk assessment completed, Disaster recover procedures defined, service level commitments and agreements finalized |  |
|  |  | Establish System Administration Functions- client copy daily check, transport, and backup and recovery procedures | IT Infrastructure Document, System Landscape Made Easy Guide, Change and Transport Request Form, Change Request Log Template, Change Request Form How To, Change Management Procedure How To, Misc links to SAPNet | System Administrator, Database Administrator, Technical Team Lead, Technical Consultant | System administration functions have been verified, tested and documented. |  |
|  |  | Set Up the Quality Assurance Environment- install the hardware, configure and secure the system, set up printing services and import change requests from the development system | IT Infrastructure Document, R/3 Security Manual, Change and Transport Request Form, Change Request Log Template, Change Request Form How To, Change Management Procedure How To, Change and Transport Request Form, Misc links to SAPNet | System, Database, Operating System, and Network Administrators; Technical Team Lead, Technical Consultant, Customer Project Manager, TeamSAP Project Manager, Business Process Team Lead | Hardware and software properly installed, printing services set up, Quality assurance system built with imports from development system | Quality assurance system ready to support project team |
|  |  | Define Production System Design, Management, and Environment | Complete Technical Questionnaires, R/3 Security Manual, IT Infrastructure Document, Define and Document Printing Infrastructure, Tuning the SAP Spool System, Misc links to SAPNet | System, Database, Operating System, and Network Administrators; Technical Team Lead, Technical Consultant, Customer Project Manager, TeamSAP Project Manager, Business Process Team Lead | Hardware and software properly installed, printing services set up, Production system built with imports verified in the quality assurance system, SAP System Operation Manual created | Production system ready to support project team |
| 4 | System Management | Establish Production System Administration | List of Reorganization System Reports, IT Infrastructure Document, Guide to Printing Infrastructure, Systems Operational Staff Training Workshops, Misc links to SAPNet | Technical Consultant, Business Process Owner, Business Process Team Lead, Power User, System, Database, Network, and Operating System Administrators | Administration procedures are setup and verified. |  |
|  |  | Conduct System Tests for printing and faxing, system administration, failure test, volume test, and stress test | Volume Test Sample Plan, Stress Test Sample Plan, Stress Testing Strategy, Define Backup Strategy, Develop Printing and Fax Test Plan, SAP GoingLive Check, Misc links to SAPNet | System, Database, and Operating System Administrators; Technical Team Lead, Technical Consultant, Customer Project Manager, TeamSAP Project Manager, Business Process Team Lead, Application Consultant, Business Process Team Member | System testing is complete. |  |
| 5 | Production Support | Provide user support and optimize system performance | Refine Production Support Plan |  |  |  |

## Define Technical Implementation Standards (Phase 1)

### Definition

Important technical issues need to be addressed and understood early in the implementation for minimal impact to the project at later stages. The management and procedures for change requests needs to be understood and setup properly. A strategy for the application of support packages to keep the SAP systems running as error-free as possible is an important consideration. A clear understanding of the upgrade procedure and options is important for making the right decisions at the right time.

### Purpose

The purpose of defining technical implementation standards is to setup a sound technical base for the implementation. Proper procedures for change management (transports), application of support packages, and an understanding of the upgrade process must be defined and understood to ensure minimal impact to the project at later stages.

### How to

The definition of technical implementation standards must be coordinated between the functional and technical teams. Communication procedures are established between the developers, customizers, and the technical staff to support the transport of change requests into other clients and systems. Activities requiring downtime, such as application of support packages and upgrades, must be decided upon to minimize downtime.

Deliverables include defining change and transform request procedures and forms. Project managers and team leads should fully understand support package and upgrade issues and options.

Roles involved are Business Process Team Lead, Customer Project Manager, TeamSAP Project Manager, Technical Team Lead, System Administrator, and Technical Consultant.

## Define System Landscape (Phase 1)

### Definition

Determine the required systems and clients and define the transport strategy.

### Purpose

The purpose of defining the system landscape is that the SAP systems must be defined and setup properly to support the project implementation in an efficient way. A large part of the implementation involves the customizing, transport, and testing of change requests. The needs for this will determine the systems and clients.

### How to

Managers and members from the functional and technical teams must meet and decide the system landscape that needs to be setup. Things to consider are the systems and clients that will be needed. Define the purpose and name for each system. Every client will have a specific role and it is necessary to define the client settings that are appropriate for the role. The IT Infrastructure Document will be maintained to document information on the SAP systems and clients.

The main deliverable is the design of the system landscape, setup, and maintenance strategy.

The roles involved are Customer Project Manager, TeamSAP Project Manager, Technical Team Lead, Technical Consultant, and System administrator.

## Technical Requirements Planning (Phase 1)

### Definition

Identify technical requirements and procure the hardware.

### Purpose

The purpose of this activity is to identify the technical infrastructure needed to implement the SAP System, and to clarify the customer’s expectations.

### How to

Complete the technical questionnaires from your and work on hardware sizing with your hardware vendor. Determine the hardware needs for all three levels (front-end, application, and database levels). Review and approve the system sizing results. Order the hardware and take into account the expected delivery times. Order the remote connection to SAP.

The deliverables are a detailed sizing of the SAP systems and technical infrastructure needs. Review and approval of the required hardware. Orders placed for the hardware and the remote connection.

Roles involved are System Administrator, Database Administrator, Operating System Administrator, Network Administrator, Technical Team Lead, Technical Consultant, Customer Project Manager, and TeamSAP Project Manager.

## Develop System Environment (Phase 2)

### Definition

Install and configure the development system. Setup the development system environment and define system administration procedures

### Purpose

The purpose of this work package is to create the technical design, setup the development system, and maintain system administration procedures.

### How to

Install, configure, and secure the development system. Setup the printing services and the desktop components for the project team. Configure the remote connection to SAP and maintain system administration procedures.

Deliverables are the hardware and software for the development system are properly installed, printing services and remote connection are setup, system administration procedures are defined, and the technical staff fully trained to support the SAP environment.

Roles involved are the System Administrator, Operating System Administrator, Database Administrator, Network Administrator, Technical Team Lead, Technical Consultant, Customer Project Manager, TeamSAP Project Manager, and Business Process Team Lead

## System Management (Phase 3)

### Definition

Install and configure the quality assurance and production systems. Develop test plans for system tests, such as volume and stress tests. Define service level agreements and disaster recovery procedures. Establish system administration, backup, and recovery procedures.

### Purpose

The purpose of this work package is to integrate the quality assurance and production systems into the SAP landscape at the proper time in the project.

### How to

Install, configure, and secure the quality assurance and production systems. Setup the printing services and the desktop components for the project team. Work with the hardware vendor to define the service level agreement. The technical team needs to establish system administration and support procedures. This should be coordinated with the project team so that maintenance and system administration work has minimal impact to the project team.

Deliverables are the failure scenarios risk assessment is complete, disaster recover procedures are defined, and service level agreements are complete. System administration functions are verified, tested, and documented. The quality assurance and production systems are ready to support the project team.

Roles involved are System Administrator, Database Administrator, Operating System Administrator, Network Administrator, Technical Team Lead, Technical Consultant, Customer Project Manager, TeamSAP Project Manager, Business Process Team Lead, Project Sponsor, and SAP Technical Consulting Manager

## System Management (Phase 4)

### Definition

Establish system administration, procedures, and system tests for the production system.

### Purpose

The purpose of this work package is to establish production system administration and to conduct system tests to verify that the SAP system is ready for productive operation.

### How to

The technical team should ensure that the standard SAP reorganization reports have been scheduled and operational. Verify CCMS in the production system and finalize system administration procedures. Documentation, such as, the IT Infrastructure Document, R/3 Security Manual, and Operations Manual should be updated to reflect the current environment. The technical team should conduct tests to verify the printing infrastructure, failure scenarios, system administration, and backup and recovery procedures. Work with the project team to conduct volume and stress tests to verify that the SAP environment can support the business processes.

Deliverables include the completion of IT Infrastructure Document, R/3 Security Manual, and Operations Manual. System testing is complete. Technical team and support staff have been trained to support the SAP productive environment.

Roles involved are System Administrator, Database Administrator, Operating System Administrator, Network Administrator, Technical Team Lead, Technical Consultant, Customer Project Manager, TeamSAP Project Manager, Business Process Team Lead, Application Consultant, Business Process Team Member, Business Process Owner, and Power User

## Production Support (Phase 5)

### Definition

Provide support for the production environment.

### Purpose

The purpose of this work package is for the technical team to support the production system in productive operation.

### How to

The technical team should work to administer and maintain the production environment for optimal performance. Fine tune escalation procedures and system administration support as required. Work with Operations, the Help Desk, and end users.

Deliverables include the refinement of all technical documentation as necessary.