## Program Management Project Methodology Overview for Global and Rollout Roadmaps

### Definition

The subject area, Program Management, contains topics that call for managing multiple concurrent projects simultaneously. These include many topics that are also associated with Project management, but differ in order of magnitude, political sensitivity, complexity, and time frame.

### Purpose

The scope of Program Management includes conventional project management, as well as providing a mission statement for global template development and the global rollout schedule for projects (at least for Phase One). Program Management is in effect worldwide and becomes the basis for global development and implementation as a whole. Program Management operates in consideration of the output from Conduct Executive Strategy Workshop and Perform Strategy Study. It is above the level of project management for a single installation, or even an entire country, having to do with the nature and content of the global template.

### Project Management Overview Table

| - Phase | - Work package or ”Activity group” | - Activities | - Tools or - Key Accelerators | - Roles | - Deliverables |
| --- | --- | --- | --- | --- | --- |
| - 1 | - Initial Project Planning | - Create Project Charter | - Industry Solution Maps with KPIs, - Sample Project Charters | - Project Sponsor, TeamSAP, Project Manager, Customer, Project Manager | - Project Charter |
|  |  | - Review and Refine Implementation Strategy | - Enterprise Area Scope Document Template | - TeamSAP/ Customer Project Manager | - Enterprise Area Scope Document |
|  |  | - Establish Project Team Working Environment | - Project Room Requirements White Paper | - TeamSAP/ Customer Project Manager | - Project Room Plan, List of office equipment needed to set up project room |
|  | - Determine Project Organization | - Finalize the Project Organization for the Implementation | - Project Organization Template | - TeamSAP/ Customer Project Manager | - Organizational Diagram of Project Organization |
|  | - Prepare Project Plan | - Prepare detailed plans to monitor the progress of the project | - Microsoft Project Plan | - TeamSAP/ Customer Project Manager | - Work Plan, Budget Plan and Resource Plan |
|  | - Project Procedures | - Define Project Management and Implementation Standards and Procedures | - Issue Database | - TeamSAP/ Customer Project Manager | - Process Description for Scope and Issue Management |
|  | - Project Kick-Off | - Company wide kick-off of the project and internal project kick-off | - Project Kick-Off Agenda Template | - TeamSAP/ Customer Project Manager - Project Sponsor |  |
| - 2 | - Business Process Definition | - Setting up workshops to determine the business processes effected by the implementation and any discrepancies from the original project scope | - Q&Adb, Application Consultants Guide | - TeamSAP/ Customer Project Manager - Application Consultants | - Business Blueprint, Change Requests, Revised Budget and Project Plan, Revised Project Organization Plan |
| - 3 | - Initial planning for production support and cutover | - Determine Production Support and Cutover Plan for the time before and after going live | - Help Desk White Paper, Cutover Process Checklist, Cutover Plan Template, Cutover Process Task Schedule | - TeamSAP/ Customer Project Manager | - Production Support Plan, Cutover Plan |
|  | - Prepare Final Integration Test | - Set up a test plan for the final integration, allocate resources, ensure that test cases are established | - CATT, test scenarios (Knowledge Corner), test scenario templates, Testing strategy white paper | - TeamSAP/ Customer Project Manager - Business Process Team Lead | - Final Integration Test Plan |
| - 4 | - Detailed Project Planning | - Review the Cutover Plan based on the information available at that stage |  | - TeamSAP/ Customer Project Manager | - Reviewed Cutover Plan |
| - 5 | - Validate Live Business Process Results | - Compare achieved results with business and project measurements as established in Phase 1 of the project | - Project Charter | - TeamSAP/ Customer Project Manager - Steercom | - Project Sign Off |

## Initial Project Planning

### Definition

- Initial project planning includes the development of a project charter, the clarification of the scope of the project. It also includes the establishment of the project room.

### Purpose

- The main purpose of Initial Project Planning is to ensure that all parties involved have the same understanding of the project objectives, targets and scope.

### How to

- To create the project charter interviews with the Steering Committee members have to be conducted to collect their input regarding business objectives, drivers, and measurements and to consolidate them into one document. The scope of the project as well as the project milestones should have been defined in the Pre-Sales phase and it is now important to confirm this information or to adjust them based on new parameters.

- To set up the project room a lot of information about the project team has to be made available. Depending on the number of sites, project members, and so on, a room and the equipment inside can be planned.

## Determine Project Organization

### Definition

- The project organization includes the Steering Committee members, the project sponsor, the project managers, and the members of the different teams

### Purpose

- The purpose of this work package is to define the people fulfilling different roles during the implementation and to inform those members about their duties, the expected deliverables, and the time necessary to fulfill these tasks.

### How to

- Based on the information available in ASAP the necessary roles for this implementation have to be identified and the necessary resources have to be allocated. Regarding the resources the past has shown different approaches and only one approach can be recommended here: Best people – best results!

## Prepare Project Plan

### Definition

- The Project Plan includes tools and / or templates to monitor the budget, the time frame as well as the resources and their deliverables.

### Purpose

- The main purpose of the Project Plan is obviously to monitor the progress of the project in the different aspects of time, quality, and time.

### How to

- Based on the original project plan (typically the MS Project plan as per ASAP) a more detailed plan to monitor the budget, the resources, and work packages has to be established. There are many different ways to develop tools and templates and most probably every Project Manager will have his own style. Also customers might want to use their own way to monitor projects.

## Project Procedures

### Definition

- Project Procedures include standards for scope and issue management, documentation, and other procedures that have to be defined at the beginning of a project.

### Purpose

- The main purpose here is make sure that all key players in the project follow the same standards and procedures to be able to monitor the progress of the project.

### How to

- Firstly, the project managers have to decide on the standards and procedures. ASAP provides quite a few tools and accelerators, such as the Issue Database, to support this process. After finalizing the concept a meeting with all project members should be organized to communicate and agree on this concept.

## Project Kick-Off

### Definition

- All parties not only involved but also effected by the project have to get informed about the objectives, time frame, and players in the implementation

### Purpose

- The main purpose here is to make everybody who will be effected by the implementation aware of the project, the main business drivers behind it and also the project measurements and members.

### How to

- If possible, all members of an organization should be invited to attend the project kick-off. It is important that the Project Sponsor, or another member of the Steering Committee, takes a leading role during the kick-off to show the commitment of the top players of the organization. A proposed agenda for such a kick-off can be found in the Implementation Assistant.

- It is of utmost importance that the kick-off is not the last event where staff members hear about the SAP System before going live. Instead a concept should be established how to inform the entire organization about the progress of the project throughout the project. Other activities to involve the organization should be considered to eventually lift the awareness level to a buying-in and ideally to a level of ownership.

## Business Process Definition

### Definition

- Business Process Definition includes the definition of all the relevant business processes of the customer, gathering of general as well as detailed information about his requirements to be able to deliver the Business Blueprint

### Purpose

- The purpose of this work package is to define the company requirements based on SAP business processes, to provide the required functions. You must first define your organizational structure.

- The business process definitions create your Business Blueprint

### How to

- To be able to compile the Business Blueprint several workshops have to be conducted:

- During the first workshop the standardization aims (general settings) have to get analyzed.

- Examples of candidates for standardization include:

- Numbering systems

- Charts of accounts

- Statistics

- Units and measurement

- Balance sheets and profitability analyses

- Handling of procedures, rules and standards for data transfer between application systems

- In the second step the requirements for the following areas have to be determined:

- Business process

- Reporting

- Interface

- Conversion

- Enhancements

- Authorization

- The business process workshops are a crucial part, as all the results gathered during the workshops subsequently create the Business Blueprint. It is necessary to use the questions in the Q&Adb to determine business requirements, and to complete a customer input template for each business process.

- Finally, detailed requirements related to business processes, and review identified deficient areas have to be identified. When conducting the detailed requirements workshop, the following topics must be considered:

- Review identified deficient areas

- Clarify requirements using demonstrations

- Last but not least, all these activities lead to the completion of the Business Blueprint, which is the main deliverable of Phase 2. The Business Blueprint serves as your conceptual master plan, and becomes a detailed written document. This document shows you the business requirements in detail, and serves as the basis for organization, configuration and, if necessary, development activities.

## Initial Project Planning for Production Support and Cutover

### Definition

- A plan has to be established for the period where the productive system gets prepared to go live and the phase afterwards

### Purpose

- The purpose here is firstly to ensure a smooth cutover to the productive system, including all activities related to the data take-on. It also includes the development of a plan to make sure that there is sufficient support for the system and the end users available after going live.

### How to

- For the cutover a plan for migrating the system and organization to a production system needs to be prepared.

- The cutover plan focuses on the activities, tasks, and timing of the final days of effort. The main benefit is a plan to ensure a smooth transition to production. Referring to this plan if difficulties arise can serve as a guide to action. The cutover plan includes a checklist that reviews points of readiness, and provides the basis for approval to progress.

- For the phase after going live the technical configuration for the productive system has to be finalized and the necessary hard- and software has to be procured.

- To ensure sufficient support when going live a production support team (for short-term support after going live) as well as a Help Desk (long term) has to be established as well as procedures and standards for disaster recovery in case of a system crash.

## Prepare Final Integration Test

### Definition

- Setting up of a Final Integration Test Plan includes test scenarios, defined roles and responsibilities and time frame

### Purpose

- The purpose of this activity is to setup test team and logistics for the final integration test, and to determine the test plan that includes:

- Test scope

- Test scenarios

- Test processes

- Timeframes for testing

- Persons responsible for testing

- The scope of the test is based on the process design for the enterprise areas as defined in the Business Blueprint. The goal of the final integration test is to simulate live business processing.

### How to

- The final integration testing is a critical task in your implementation. Your test plan must include the following processes and components:

- Business process

- Output

- Reports

- Interfaces

- Conversions

- Enhancements

- Technical setup (Printer, fax)

- Authorization

The final integration test plan ensures quality, and that everything defined in the Business Blueprint is tested. Identify the necessary processes and associated dependencies. Create a timeline outlining tests according to their sequence and dependencies.

This procedure describes how you prepare the integration test plan. Integration testing encompasses areas that cross departmental boundaries, bringing together the efforts of previous tasks. The objective is to build on what has already been developed.

The final integration test is process-oriented and conducted by the responsible business process owners. It is useful to involve the extended team members in this test. Although the extended team members may be new to the project thus requiring some initial SAP system training, they provide two benefits: fresh outlook and closer knowledge of the business processes.

## Detailed Project Planning

### Definition

Review of the Cutover Plan as established earlier

### Purpose

The purpose of this activity is to ensure that new information, such as delays in the delivery of documents, resources not available, and so on, are incorporated into the Cutover Plan prepared earlier in the project.

## Validate Live Business Results

### Definition

Compare achieved results with business and project measurements as defined in Phase 1

### Purpose

The purpose of this activity is to make sure and document that the objectives defined at the beginning of the project were fulfilled.

### How to

The easiest part here is to compare the planned time frame and the agreed budget with the actual figures. Regarding the business measurements it might be difficult to see the results immediately after going live since it might take some time until everything is stable and fully working.